## Sheet1
PRODUCT BACKLOG : AGME Online booking services
| ID | PRODUCT BACKLOG ITEM | USER STORY | OWNER | PRIORITY | EFFORT in story points | Status | DEFINITION OF DONE | NOTES
Aldo | 1 | Regestering for customers | As a, customer I want to, sign up so that, I can use the functionality | Scrum team | Critical | 5 | In Progress | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Aldo | 2 | Login feature for customers | As a, customer I want to, login so that, I can make bookings | Scrum team | Critical | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Aldo | 3 | View profile feature for customers | As a, customer I want to, View profile so that, I can see my personal information | Scrum team | Medium | 8 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Aldo | 4 | Edit profile feature for customers | As a, customer I want to, edit my profile so that, I can make sure my information is up-to-date | Scrum team | Medium | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Negar | 5 | Customers can book an appointment for any service on the portal | As a, customer I want to, make bookings so that, I can receive a service | Scrum team | Critical | 8 | In Progress | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Negar | 6 | Customers can delete any booking made 48 hours before the serivice is due to be provided | As a, customer I want to, Delete bookings so that, I can cancel my booking | Scrum team | High | 3 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Negar | 7 | Customers are able to view available days/times, services and worker who is providing service | As a, customer I want to, View available days/times, services and worker who is providing service so that, I can choose what suits me | Scrum team | Low | 8 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Negar | 8 | Customers are able to view the past months bookings they have made | As a, customer I want to, View my booking history so that, I can check past appointments (and choose the same service again) | Scrum team | Low | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Alek | 9 | Regestering for admin | As a, Admin user (business owner) I want to, sign up so that, my business can have an online booking system | Scrum team | Critical | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Alek | 10 | Login feature for admin | As a, Admin user (business owner) I want to, login so that, I can view bookings, clients and workers. as well as being able to create/edit/delete worker profiles and add/edit time/dates | Scrum team | Critical | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Alek | 11 | Regestering employees feature for admin | As a, Admin user (business owner) I want to, create workers so that, I can assign them to customers for a service | Scrum team | Medium | 8 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Alek | 12 | Edit emplyee feature for admin | As a, Admin user (business owner) I want to, edit worker so that, I can keep information updated | Scrum team | Low | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Amy | 13 | Delete worker feature for admin | As a, Admin user (business owner) I want to, delete workers so that, I can remove redundant workers | Scrum team | Low | 3 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Amy | 14 | Register working time/dates feature for the businness - admin only | As a, Admin user (business owner) I want to, add working time/dates so that, my business shows all available times for clients | Scrum team | Medium | 8 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Amy | 15 | Edit working time/dates feature for the businness - admin only | As a, Admin user (business owner) I want to, edit working time/dates so that, my business displays the most uptodate information | Scrum team | Low | 8 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Amy | 16 | View past bookings from the previous month feature for admin | As a, Admin user (business owner) I want to, view past bookings so that, my business can learn from the data analytics, legal reasons, or unhappy customers | Scrum team | Low | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Richard | 17 | View new bookings feature for admin | As a, Admin user (business owner) I want to, view new bookings so that, my business can plan to provide future services | Scrum team | Critical | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Richard | 18 | View worker availability feature for admin | As a, Admin user (business owner) I want to, view worker availability so that, I can schedule jobs accordingly | Scrum team | Low | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Richard | 19 | Login feature for workers | As a, worker I want to, login so that, I can view bookings for jobs i've been allocated | Scrum team | Low | 5 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Richard | 20 | Workers can view assigned working hours/days and services | As a, Worker I want to, view assigned working hours/days and services so that, I know what jobs I have to do | Scrum team | Low | 3 | Not started | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Amy | 21 | UML Diagram |  | Scrum team | High | 5 | In Progress | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors
Negar | 22 | Wireframes |  | Scrum team | High | 5 | In Progress | Produced code, unit tests have been written and passed, functional test passed, automated acceptance tests (based on the acceptance criteria of the user story) are conducted and passed, Project Deployed on Test Environment, tests on web-based server have been done, tested on appropriate mobile device , tested on desktop device, usability review, Code is refactored, Code is peer reviewed through Github, Feature functionality confirmed and checked by Product Owner, Project builds without errors